## Fall
GANTT CHART | [24 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | LIDC-IRDI Classification
[5 empty] | PHASE ONE | [34 empty] | PHASE TWO | [41 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01
[5 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
Project Team Composition | All | 2025-08-25 | 2025-09-12 | 17 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
Project Proposal |  |  |  |  | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
Introduction & Background | Kai Hackney | 2025-09-13 | 2025-10-01 | 18 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
Problem Definition | Bryan Shook | 2025-09-18 | 2025-10-01 | 13 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
Methods | Jason Yu & Yash Agrawal | 2025-09-13 | 2025-10-01 | 18 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
Potential Dataset | Kai Hackney | 2025-09-21 | 2025-10-01 | 10 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
Potential Results & Discussion | Andrew Brown | 2025-09-21 | 2025-10-01 | 10 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
Video Creation & Recording | All | 2025-09-25 | 2025-10-03 | 8 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
GitHub Page | Kai Hackney | 2025-09-25 | 2025-10-03 | 8 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
Midterm Report |  |  |  |  | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
CNN (M1) Design & Selection | Yash Agrawal | 2025-10-08 | 2025-10-12 | 4 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
CNN Data Cleaning | Yash, Andrew | 2025-10-13 | 2025-10-17 | 4 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
CNN Data Visualization | Jason Yu | 2025-10-15 | 2025-10-19 | 4 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
CNN Data Transformation | Andrew Brown | 2025-10-17 | 2025-10-22 | 5 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
CNN Implementation & Coding | Yash Agrawal | 2025-10-20 | 2025-10-29 | 9 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
CNN Hyperparamter Tuning | Kai Hackney | 2025-10-20 | 2025-11-02 | 12 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
CNN Results Evaluation | Jason Yu | 2025-10-27 | 2025-11-02 | 5 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
Random Forest (M2) Design & Selection | Yash Agrawal | 2025-10-08 | 2025-10-12 | 4 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
Random Forest Data Cleaning | Yash, Andrew | 2025-10-13 | 2025-10-17 | 4 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
Random Forest Data Visualization | Jason Yu | 2025-10-15 | 2025-10-19 | 4 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
Random Forest Data Transformation | Andrew Brown | 2025-10-17 | 2025-10-22 | 5 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
Random Forest Implementation & Coding | Yash Agrawal | 2025-10-20 | 2025-10-29 | 9 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
Random Forest Hyperparamter Tuning | Kai Hackney | 2025-10-20 | 2025-11-02 | 12 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
Random Forest Results Evaluation | Jason Yu | 2025-10-27 | 2025-11-02 | 5 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
NN (M3) Design & Selection | Yash Agrawal | 2025-10-08 | 2025-10-12 | 4 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
NN Data Cleaning | Yash, Andrew | 2025-10-13 | 2025-10-17 | 4 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
NN Data Visualization | Jason Yu | 2025-10-14 | 2025-10-19 | 5 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
NN Data Transformation | Andrew Brown | 2025-10-15 | 2025-10-22 | 7 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
NN Implementation & Coding | Yash Agrawal | 2025-10-16 | 2025-10-29 | 13 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
NN Hyperparamter Tuning | Kai Hackney | 2025-10-20 | 2025-11-02 | 12 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
NN Results Evaluation | Jason Yu | 2025-10-17 | 2025-11-02 | 15 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
Midterm Report | Bryan, Jason | 2025-10-18 | 2025-11-07 | 19 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
Final Report |  |  |  |  | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
K-Means (M4) Design & Selection | Yash, Jason, Bryan | 2025-11-08 | 2025-11-11 | 3 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
K-Means Data Cleaning | Kai Hackney | 2025-11-12 | 2025-11-16 | 4 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
K-Means Data Visualization | Jason Yu | 2025-11-14 | 2025-11-18 | 4 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
K-Means Feature Reduction | Bryan Shook | 2025-11-16 | 2025-11-20 | 4 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
K-Means Coding & Implementation | Andrew Brown | 2025-11-19 | 2025-11-23 | 4 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
K-Means Results Evaluation | All | 2025-11-21 | 2025-11-25 | 4 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
M2-M3 and M(2+4) - M(3+4) Comparison | All | 2025-11-21 | 2025-11-25 | 4 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving
Video Creation & Recording | All | 2025-11-29 | 2025-12-02 | 3 | 2025-10-06 M: Break; 2025-11-24 R: Thanksgiving
Final Report | All | 2025-11-29 | 2025-12-02 | 3 | 2025-10-06 M: Fall; 2025-11-24 R: Thanksgiving

## Fall Overview
GANTT CHART | [7 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | NLST Classification
[5 empty] | PHASE ONE |  | PHASE TWO | [5 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2025-09-15 | 2025-09-22 | 2025-09-29 |  | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24
Project Proposal |  | 2025-09-13 | 2025-10-03 | 20
Introduction & Background | Karishma | 2021-09-27 | 2021-10-04 | 7
Problem Definition | Tim | 2021-09-27 | 2021-10-04 | 7
Methods | Bryan | 2021-09-27 | 2021-10-04 | 7
Potential Results & Discussion | Noah & Gabby | 2021-09-27 | 2021-10-04 | 7
Video Recording | All | 2021-10-04 | 2021-10-07 | 3
GitHub Page | Karishma | 2021-10-04 | 2021-10-07 | 3
CNN |  | 2025-10-08 | 2025-11-07 | 29
Data Sourcing and Cleaning | Tim | 2021-10-07 | 2021-10-15 | 8
Model Selection | Karishma | 2021-10-15 | 2021-10-18 | 3
Data Pre-Processing | Tim | 2021-10-18 | 2021-10-25 | 7
Model Coding | Karishma | 2021-10-25 | 2021-11-08 | 13
Results Evaluation and Analysis | Tim | 2021-11-08 | 2021-11-16 | 8
Midterm Report | All | 2021-11-08 | 2021-11-16 | 8
Random Forest |  | 2025-10-08 | 2025-11-07 | 29
NN |  | 2025-10-08 | 2025-11-07 | 29
Data Sourcing and Cleaning | Gabby | 2021-10-18 | 2021-10-22 | 4
Model Selection | Noah | 2021-10-22 | 2021-10-25 | 3
Data Pre-Processing | Gabby | 2021-10-25 | 2021-10-29 | 4
Model Coding | Noah | 2021-10-25 | 2021-11-19 | 24
Results Evaluation and Analysis | Gabby | 2021-11-19 | 2021-11-24 | 5
K-Means |  | 2025-11-08 | 2025-11-25 | 17
Data Sourcing and Cleaning | Bryan | 2021-10-18 | 2021-10-22 | 4
Model Selection | Bryan | 2021-10-22 | 2021-10-25 | 3
Data Pre-Processing | Bryan | 2021-10-25 | 2021-10-29 | 4
Model Coding | Bryan | 2021-10-25 | 2021-11-19 | 24
Results Evaluation and Analysis | Bryan | 2021-11-19 | 2021-11-24 | 5
Evaluation |  | 2025-11-24 | 2025-12-02 | 8
Model Comparison | Tim | 2021-11-29 | 2021-12-07 | 8
Presentation | All | 2021-11-29 | 2021-12-06 | 7
Recording | All | 2021-12-06 | 2021-12-07 | 1
Final Report | All | 2021-11-29 | 2021-12-07 | 8